## Work Plan
Grant Making Calendar
| Project Name: | Nigeria Round 3 Grant Making | [6 empty] | How to use template: 1. Enter project name and start date, 2. Enter tasks and phases, number of BUSINESS days required, and any other info 3. Do not edit Task Start Date/Task End Date
| Start Date: | 2021-06-07
Y Q | Phase Name | Task Description | Unit Responsible | Working Days Required | Travel Required? | Completed | Task Start Date | Task End Date
2021 Q2 | Call for EoIs | Strategy Written | PMU | 25 | NO |  | 2021-06-07 | 2021-07-12
2021 Q3 | Call for EoIs | Stratgey Submitted for consultation and approved | PMU | 43 | NO |  | 2021-07-12 | 2021-09-09
2021 Q3 | Call for EoIs | Call for EOI launched | PMU | 15 | NO |  | 2021-09-09 | 2021-09-30
2021 Q3 | Call for EoIs | GCERF EoI assessment | PMU/Fin/P&I | 5 | NO |  | 2021-09-30 | 2021-10-07
2021 Q4 | Call for EoIs | CSM review EOI shortlist | PMU | 5 | NO |  | 2021-10-07 | 2021-10-14
2021 Q4 | Call for EoIs | GCERF consolidate shortlist and notify applicants | PMU | 2 | NO |  | 2021-10-14 | 2021-10-18
2021 Q4 | Call for EoIs | Compile feedback and prepare assessment report | PMU/Fin/P&I | 0.5 | NO |  | 2021-10-18 | 2021-10-18
2021 Q4 | Due Diligence | Invite for due diligence | PMU/Finance | 0 | NO |  | 2021-10-18 | 2021-10-18
2021 Q4 | Due Diligence | Initial anti-terrorism screening | PMU | 1 | NO |  | 2021-10-18 | 2021-10-19
2021 Q4 | Due Diligence | Conduct Due Diligence in-country | PMU/Finance | 5 | NO |  | 2021-10-19 | 2021-10-26
2021 Q4 | Due Diligence | Draft Selection Report | PMU/Finance | 2 | NO |  | 2021-10-26 | 2021-10-28
2021 Q4 | Due Diligence | Share conclusion with CSM/RFP and provide feedback to applicants | PMU | 0 | NO |  | 2021-10-28 | 2021-10-28
2021 Q4 | Proposal Development | Provide Proposal Document Package to PRs, including Pre-Grant Conditions | PMU/Finance | 1 | NO |  | 2021-10-28 | 2021-10-29
2021 Q4 | Proposal Development | Share background info on PRs with IRP (for info) and share grant agreement docs with PRs for review and comment | PMU | 0 | NO |  | 2021-10-29 | 2021-10-29
2021 Q4 | Proposal Development | PRs prepare Theory of Change | PMU/Fin/P&I | 3 | NO |  | 2021-10-29 | 2021-11-03
2021 Q4 | Proposal Development | First Proposal development workshop online | PMU/Fin/P&I | 3 | NO |  | 2021-11-03 | 2021-11-08
2021 Q4 | Proposal Development | PRs submit second draft ToC and prepare Workplan | PMU/Fin/P&I | 7 | NO |  | 2021-11-08 | 2021-11-17
2021 Q4 | Proposal Development | Second Proposal development workshop online | PMU | 2 | NO |  | 2021-11-17 | 2021-11-19
2021 Q4 | Proposal Development | PRs submit proposal documents and first budget draft | PMU/Fin/P&I | 10 | NO |  | 2021-11-19 | 2021-12-03
2021 Q4 | Proposal Development | Compile feedback on propasal and budget and share with PRs | PMU/Fin/P&I | 3 | NO |  | 2021-12-03 | 2021-12-08
2021 Q4 | Proposal Development | PRs submit final proposals / second budget draft | PMU | 5 | NO |  | 2021-12-08 | 2021-12-15
2021 Q4 | Proposal Development | Send proposals to Head PMU, IRP, and CSM for review | PMU | 5 | NO |  | 2021-12-15 | 2021-12-22
2021 Q4 | Proposal Development | Final changes to proposals / Budget finalised | PMU/Fin/P&I | 5 | NO |  | 2021-12-22 | 2021-12-29
2021 Q4 | Proposal Development |  |  | 0 | NO |  | 2021-12-29 | 2021-12-29
2021 Q4 | Proposal Development | Sign off on pre-grant conditions and any STCs | PMU/Fin/P&I | 1 | NO |  | 2021-12-29 | 2021-12-30
2021 Q4 | Proposal Development | Budget approved / Prepare draft grant agreements | Fin/PM | 2 | NO |  | 2021-12-30 | 2022-01-03
2022 Q1 | Proposal Development |  | PMU | 0 | NO |  | 2022-01-03 | 2022-01-03
2022 Q1 | Proposal Development | APPROVAL PROCESS, FINAL SIGNATURE, SIGNING CEREMONY | PMU | 2 | NO |  | 2022-01-03 | 2022-01-05
2022 Q1 | Proposal Development | Process GAD expense requests | Fin | 3 | NO |  | 2022-01-05 | 2022-01-10
2022 Q1 | Proposal Development | Disburse GAD expense payments | Fin | 1 | NO |  | 2022-01-10 | 2022-01-11
2022 Q1 |  | POTENTIAL PROGRAMME START DATE |  | 1 | NO |  | 2022-01-11 | 2022-01-12
Formulas:
Task Start Date = IF([Task End Date, row above]=0,[Task Start Date, row above],[Task End Date, row above])
Task End Date = WORKDAY([Task Start Date],[Working Days Required])

## Sheet1
YES
NO